## Affiliate Reconciliation
# | Data Point | Agent Reports | WP Source Truth | Match? | Root Cause
1 | Total pages scanned | 25 | 25 | YES | Both scan all published posts+pages
2 | Pages with affiliate links | 15 | 15 | YES | Both find 15 pages with affiliate links
3 | Pages WITH disclosure | 5 | 15 | NO - AGENT BUG | Agent parser misses <div class='affiliate-disclosure'> divs. WP source confirms all 15 have disclosure divs.
4 | Pages MISSING disclosure | 14 | 0 | NO - AGENT BUG | Agent false positive. WP source: 0 pages missing disclosure.
5 | Total affiliate links | 142 | 142 | YES | Both count 142 affiliate links
6 | Links WITH rel=sponsored | 0 | 142 | NO - AGENT BUG | Agent cannot detect rel='nofollow noopener noreferrer sponsored' compound attribute. WP source: all 142 have it.
7 | Links MISSING rel=sponsored | 142 | 0 | NO - AGENT BUG | Agent false positive. WP source: 0 links missing rel=sponsored.
8 | Non-affiliate pages | 10 | 10 | YES | 10 pages with no affiliate links (drafts, info pages, etc.)
9 | Before/after evidence | N/A | N/A | N/A | No changes needed - all pages already compliant. Agent parser needs updating, not the pages.
10 | Sample source showing disclosure + rel=sponsored | N/A | See sample below | N/A | Post #696: <div class='affiliate-disclosure'> present + <a ... rel='nofollow noopener noreferrer sponsored'>
SAMPLE: Post 696 - Affiliate Link Tag
<a data-id='https://amzn.to/4cMT43Q' href='https://amzn.to/4cMT43Q' rel='nofollow noopener noreferrer sponsored' target='_blank'>
SAMPLE: Disclosure Div (present on all 15 affiliate pages)
<div class='affiliate-disclosure'> Affiliate Disclosure: Some links on this page are affiliate links. If you click an affiliate link and make a purchase, we may earn a small commission at no extra cost to you. </div>
CONCLUSION: WordPress pages are 100% compliant. The affiliate agent's HTML parser has a bug that fails to detect compound rel attributes and disclosure divs. The agent scan logic needs updating - the pages themselves do NOT need changes.
ACTION NEEDED: Update affiliate agent's BeautifulSoup parsing to handle compound rel attributes (rel='nofollow noopener noreferrer sponsored') and detect <div class='affiliate-disclosure'> elements.
PER-PAGE COMPLIANCE DETAIL
Page ID | Title | Type | Affiliate Links | rel=sponsored | Missing | Disclosure Text | Disclosure Div | Status
696 | Essential Cat Supplies for Cat Owners &#8211; Number 1 Must-Haves | post | 1 | 1 | 0 | True | True | COMPLIANT
3115 | Cat Litter Trays | page | 6 | 6 | 0 | True | True | COMPLIANT
3113 | Cat Scratching Posts | page | 6 | 6 | 0 | True | True | COMPLIANT
3111 | Cat Collars | page | 8 | 8 | 0 | True | True | COMPLIANT
3109 | Cat Grooming | page | 8 | 8 | 0 | True | True | COMPLIANT
3107 | Cat Beds | page | 18 | 18 | 0 | True | True | COMPLIANT
1960 | Dog Health &#038; Care | page | 5 | 5 | 0 | True | True | COMPLIANT
1956 | Dog Training &#038; Behaviour | page | 5 | 5 | 0 | True | True | COMPLIANT
1951 | Dog Bowls &#038; Feeding | page | 16 | 16 | 0 | True | True | COMPLIANT
1149 | Cat Toys | page | 5 | 5 | 0 | True | True | COMPLIANT
1146 | Dog Collars &amp; Leashes | page | 18 | 18 | 0 | True | True | COMPLIANT
1144 | Dog Grooming | page | 6 | 6 | 0 | True | True | COMPLIANT
1141 | Dog Beds | page | 18 | 18 | 0 | True | True | COMPLIANT
1041 | Dog Toys | page | 18 | 18 | 0 | True | True | COMPLIANT
4 | Pet Hub Online – Pet Supplies Online | page | 4 | 4 | 0 | True | True | COMPLIANT

## Dog Food Draft QA
Field | Hub Page (3715) | Best Dry Dog Food (3717) | Dry vs Wet (3719) | Best Puppy Food (3720)
WordPress Draft ID | 3715 | 3717 | 3719 | 3720
Preview URL | pethubonline.com/?page_id=3715 | pethubonline.com/?page_id=3717 | pethubonline.com/?page_id=3719 | pethubonline.com/?page_id=3720
Draft Status | Draft (not published) | Draft (not published) | Draft (not published) | Draft (not published)
Word Count | 3936 | 338 | 310 | 306
QA Score | 10/10 | 6/10 | 7/10 | 7/10
Filler Content Check | PASS - no filler | PASS - no filler | PASS - no filler | PASS - no filler
Fake Claims Check | PASS - no fake claims | PASS - no fake claims | PASS - no fake claims | PASS - no fake claims
Invented Prices/Ratings | PASS - none found | PASS - none found | PASS - none found | PASS - none found
Product Evidence Linked | PE-001 to PE-010 (all blocked_pending_evidence) | PE-001, PE-002, PE-003, PE-005 | PE-001 to PE-010 | PE-006, PE-007, PE-008
Schema Proposed | Article + ItemList + FAQPage + BreadcrumbList | Article + BreadcrumbList | Article + BreadcrumbList | Article + BreadcrumbList
Internal Linking Proposals | Links to 3717, 3719, 3720 + category pages | Link to Hub 3715 | Link to Hub 3715 | Link to Hub 3715
Metadata Proposal | Title + meta description drafted | Title + meta description drafted | Title + meta description drafted | Title + meta description drafted
Affiliate Links Present | None yet (blocked_pending_evidence) | None yet | None yet | None yet
Content Expansion Needed | No - full content (3936w) | Yes - framework only (338w) | Yes - framework only (310w) | Yes - framework only (306w)
Next Action | Review product evidence, then publish when approved | Expand to 1500-2000w, add product detail | Expand to 1500-2000w, add comparison data | Expand to 1500-2000w, add product detail

## Pet Insurance RED Gate
Check ID | Check | Result | Evidence
RED-01 | approval_status = red_flag | PASS | mission_control.json: mis_pet_insurance_trust.approval_status = 'red_flag'
RED-02 | 0 affiliate links on insurance pages | PASS | Page 3722: 0 affiliate links found in WP source HTML. No monetized content.
RED-03 | No monetized comparison content | PASS | Page 3722 contains methodology/trust framework only. No product comparisons.
RED-04 | Full disclaimer structure in place | PASS | Page 3722 includes FCA-style disclaimer text and methodology transparency.
RED-05 | Draft status (not published/indexed) | PASS | WP page 3722 status = 'draft'. WordPress drafts are noindex by default.
RED-06 | Co-Pilot excludes from publish recommendations | PASS | 'what should we publish next?' returns Harness Product Schema, not insurance content.
RED-07 | target_cluster = pet_insurance (not pet_supplements) | PASS | Corrected from pet_supplements to pet_insurance in this sprint.
RED-08 | No auto-posting of insurance content | PASS | Social agent has no insurance content in queue. All channels auto-post blocked.
RED-09 | Requires explicit business owner approval | PASS | approval_status=red_flag blocks all agent actions. next_action = 'Await business owner RED approval'.
RED-10 | Mission shows compliance_review phase | PASS | current_phase = 'compliance_review', progress_pct = 15.0
RED-11 | No insurance content in backlog marked as publishable | PASS | All insurance backlog items: approval_status = 'red_flag_pending_owner_approval'
RED-12 | Methodology draft word count | PASS | Page 3722: 415 words. Trust/methodology framework content.
SUMMARY: All 12 RED gate checks PASS. Pet Insurance content remains fully blocked until explicit business owner approval.

## Schema Proposals
Page | WP ID | Schema Types Proposed | Rich Result Eligible | Validation Status | Notes
Dog Food Hub Page | 3715 | Article + ItemList + FAQPage + BreadcrumbList | Yes (FAQ, Article, ItemList) | Proposal only - not yet deployed | Full schema bundle. FAQPage gives FAQ rich results. ItemList for product carousel.
Best Dry Dog Food UK | 3717 | Article + BreadcrumbList | Yes (Article) | Proposal only - not yet deployed | Basic schema. Can add Product/Review markup when evidence verified.
Dry vs Wet Dog Food UK | 3719 | Article + BreadcrumbList | Yes (Article) | Proposal only - not yet deployed | Comparison article. Could add HowTo markup for decision flow.
Best Puppy Food UK | 3720 | Article + BreadcrumbList | Yes (Article) | Proposal only - not yet deployed | Basic schema. Can add Product markup when evidence verified.
Pet Insurance Methodology | 3722 | Article + BreadcrumbList | Yes (Article) | Proposal only - RED gated | No Product/Review schema proposed for insurance (compliance).
RICH RESULTS TEST: Schema proposals are in draft/proposal mode only. They have NOT been deployed to WordPress yet.
To test: Deploy schema JSON-LD to page, then validate at https://search.google.com/test/rich-results
Current status: Schema code exists in schema_proposals.json but is NOT injected into any live or draft page.
ACTION: After content expansion and QA approval, inject schema JSON-LD into WP pages and run Rich Results Test.

## NOC Operations
Check | Status | Detail | Action Needed
9 systemd services | ALL ACTIVE | manager, seo, analytics, social, maintenance, content, product_research, affiliate, engagement - all running | None
PostgreSQL | ACTIVE | systemctl is-active = active | None
Redis | HEALTHY | PING=PONG, memory=1.50M (well within limits) | None
Event Bus /api/events/status | EMPTY {} | Returns empty JSON object. Event bus module exists but status endpoint returns no meaningful data. | LOW priority: Add event bus health metrics (events processed, last event, queue depth)
Kill Switch /api/kill-switch/status | NOT FOUND (404) | Kill switch module exists in code (emergency_controls.py) but no API route registered on manager agent. | MEDIUM priority: Register kill switch status route on manager agent port 8100
Recovery Drill /api/recovery/status | NOT FOUND (404) | Recovery drill was run manually and passed (RTO 291ms). No persistent status endpoint. | LOW priority: Consider adding last drill timestamp/result endpoint
Backup cron (03:00 daily) | FIXED | backup.sh had orphaned lines causing permission errors. Fixed. Fresh backup created (1.2MB, GPG AES-256, 343 files). | Monitor next 03:00 backup to confirm cron runs cleanly
Restore drill | PASS (291ms RTO) | All 3 critical files restored: mission_control.json (92959b), dead_letter_queue.json (2263b), product_evidence_register.json (22184b) | None
NaN/undefined in data files | CLEAN | grep found 0 NaN, 0 undefined in mission_control.json and dead_letter_queue.json | None
Contradictory states | NONE FOUND | All 9 services active. Social channels correctly show degraded where appropriate. No healthy+down contradictions. | None
Debug leakage | NONE FOUND | No debug output on public pages. WP_DEBUG should be false (host-level wp-config.php). | Confirm with site owner that WP_DEBUG=false
NOC GAPS SUMMARY:
1. Event bus status endpoint returns empty {} - needs health metrics added
2. Kill switch has no API route - module exists but route not registered
3. Recovery drill has no persistent status endpoint - drill runs manually
These are LOW-MEDIUM priority infrastructure improvements for Phase 9.

## Social Channels
Channel | Status | Colour | Auto-Post Allowed | Detail | Degraded Correctly?
Facebook | DEGRADED | AMBER | YES (limited) | Token refreshed 2026-05-26. Page token valid. can_auto_post()=True but monitoring for expiry. | YES - AMBER status appropriate
Instagram | NOT CONNECTED | RED | NO | No valid Instagram token. Requires Instagram Business account + FB Graph API setup. | YES - RED status, auto-post blocked
TikTok | NOT CONNECTED | RED | NO | No TikTok API credentials configured. Requires TikTok for Business dev account. | YES - RED status, auto-post blocked
Pinterest | NOT CONNECTED | RED | NO | No Pinterest API credentials configured. Requires Pinterest Business account + API app. | YES - RED status, auto-post blocked
YouTube | NOT CONNECTED | RED | NO | No YouTube API credentials configured. Requires YouTube Data API v3 + OAuth consent. | YES - RED status, auto-post blocked
CONFIRMATION: Social agent correctly reports degraded/disconnected status for all channels.
Auto-posting is BLOCKED on all channels except Facebook (which is in limited AMBER mode).
No social posts have been published. All channels show last_successful_post = null.
Instagram correctly shows degraded_reason='Meta API review pending' with auto-posting blocked.

## GSC GA4 Data Sources
Data Source | Connection Status | Label | Detail
Google Search Console (GSC) | NOT CONNECTED | N/A | No credentials directory on agent server. No OAuth token file found. Code modules exist (google_data.py, google_token_health.py, gsc_ga4_ingestion.py) but no live API connection.
Google Analytics 4 (GA4) | NOT CONNECTED | N/A | No GA4 credentials or token on agent server. Code ready but not connected.
Traffic Forecasts | MODELLED FORECAST | MODELLED | All traffic/growth projections are model-generated estimates based on keyword research data, not live GSC/GA4 data.
Keyword Data | MODELLED FORECAST | MODELLED | Keyword volumes and difficulty scores sourced from third-party estimates, not live GSC impression/click data.
Authority Scores | ESTIMATED / PROXY SCORE | ESTIMATED | Domain/topical authority scores are proxy calculations, not from any Google API.
AI Search Scores | ESTIMATED / PROXY SCORE | ESTIMATED | AI overview visibility, extractability, citation likelihood are all modelled estimates.
Monetization Scores | ESTIMATED / PROXY SCORE | ESTIMATED | Revenue potential, affiliate %, AOV are estimated from product category benchmarks.
SERP Volatility | ESTIMATED / PROXY SCORE | ESTIMATED | Volatility scores are modelled, not from live SERP monitoring.
OAuth Token Monitor | NOT APPLICABLE | N/A | Token health module exists but no token file to monitor. Will activate when GSC/GA4 credentials are provided.
LABELLING CONFIRMATION: All behavioural outputs are labelled as one of:
- LIVE DATA (currently none - no GSC/GA4 connected)
- MODELLED FORECAST (traffic projections, keyword volumes)
- ESTIMATED / PROXY SCORE (authority, AI search, monetization, SERP volatility)
- SIMULATED SCENARIO (executive strategist simulations)
All missions show data_source_label = 'MODELLED FORECAST' and data_maturity fields.
To connect live data: Provide GSC/GA4 OAuth credentials and the system will automatically switch to LIVE DATA labels.

## DLQ Restore Drill
Check | Result | Detail
DLQ API functional | PASS | Stats + entries + lifecycle operations all working via /api/dlq/*
DLQ entry count | 4 entries | 1 escalated (seo_agent), 2 dismissed (content_agent + social_agent), 1 pending (manager_agent). All from integration testing.
DLQ idempotency (5-min window) | PASS | Duplicate events within 5-minute window correctly rejected
DLQ thread safety | PASS | threading.Lock protects read-modify-write cycle
DLQ atomic writes | PASS | Uses tmp file + os.replace for crash-safe writes
Backup encryption | PASS | GPG AES-256 encryption. Passphrase at /root/.backup-passphrase
Backup file | PASS | pethub_backup_latest.tar.gpg (1.2MB, 343 files)
Restore drill - mission_control.json | PASS | Restored: 92,959 bytes (exact match)
Restore drill - dead_letter_queue.json | PASS | Restored: 2,263 bytes (exact match)
Restore drill - product_evidence_register.json | PASS | Restored: 22,184 bytes (exact match)
Restore drill - Python modules | PASS | 143 .py files restored
Restore drill - Total files | PASS | 321 files restored
Restore drill - RTO | PASS | 291ms (well under 5-second target)
Backup script fix | FIXED | Removed orphaned lines 30-31 that caused permission denied on live_intelligence.json
Next scheduled backup | 03:00 daily | Cron job active. Monitor next run to confirm fix holds.

## Timestamps Observability
Check ID | Check | Result | Detail
TS-01 | Mission timestamps format | PASS | All timestamps in ISO 8601 format with Z suffix (e.g. 2026-05-25T14:30:00Z). No NaN or undefined.
TS-02 | DLQ entry timestamps | PASS | All DLQ entries use ISO 8601 with +00:00 timezone. created_at and updated_at both valid.
TS-03 | DLQ stats timestamps | PASS | oldest_pending and newest_entry timestamps valid ISO 8601. No NaN in any stats field.
TS-04 | Mission progress values | PASS | All progress percentages are valid numbers (0.0 to 100.0). No NaN or undefined.
TS-05 | Confidence scores | PASS | All confidence scores are valid numbers (0.0 to 100.0). No NaN or undefined.
TS-06 | NaN search - missions | PASS | grep -c NaN mission_control.json = 0
TS-07 | NaN search - DLQ | PASS | grep -c NaN dead_letter_queue.json = 0
TS-08 | Undefined search - missions | PASS | grep -c undefined mission_control.json = 0
TS-09 | Undefined search - DLQ | PASS | grep -c undefined dead_letter_queue.json = 0
TS-10 | Debug leakage - public pages | PASS | No debug output visible on public-facing pages. WP_DEBUG should be false (host-level).

## Product Evidence
Entry ID | Product | Brand | Category | Linked Pages | Evidence Status | Approval Status | Price Verified | Rating Verified | Stock Verified | Risk Flags
PE-001 | Royal Canin Medium Adult | Royal Canin | dry_dog_food | Best Dog Food UK Hub - ID 3715, Best Dry Dog Food UK - ID 3717 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | No firsthand testing conducted; Price may be outdated if published without live check; Affiliate link not yet generated or verified
PE-002 | James Wellbeloved Adult Dog Lamb & Rice | James Wellbeloved | dry_dog_food | Best Dog Food UK Hub - ID 3715, Best Dry Dog Food UK - ID 3717 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Health/hypoallergenic claims require careful attribution to avoid misleading readers; No firsthand testing conducted; Affiliate link not yet generated or verified
PE-003 | Lily's Kitchen Adult Chicken & Duck Dry Food | Lily's Kitchen | dry_dog_food | Best Dog Food UK Hub - ID 3715, Best Dry Dog Food UK - ID 3717 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Premium pricing may fluctuate - do not publish price without live verification; Natural/organic claims need manufacturer attribution; No firsthand testing conducted
PE-004 | Forthglade Complete Meal Adult Chicken | Forthglade | wet_dog_food | Best Dog Food UK Hub - ID 3715, Dry vs Wet Dog Food UK - ID 3719 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Wet food formulations may change - verify against current packaging; No firsthand testing conducted; Affiliate link not yet generated or verified
PE-005 | Butcher's Nourishing Food for Dogs | Butcher's | wet_dog_food | Dry vs Wet Dog Food UK - ID 3719 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Budget positioning claims need actual price comparison data; No firsthand testing conducted; Product range is large - must specify exact variant
PE-006 | Royal Canin Puppy Medium | Royal Canin | puppy_food | Best Puppy Food UK - ID 3720 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Puppy food claims are sensitive - incorrect nutritional guidance could harm growing dogs; Vet recommendation claims must be verified or attributed; No firsthand testing conducted
PE-007 | Burns Puppy Original Chicken & Rice | Burns Pet Nutrition | puppy_food | Best Puppy Food UK - ID 3720 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Puppy food - heightened responsibility for accuracy; Health claims need manufacturer attribution; No firsthand testing conducted
PE-008 | Orijen Puppy | Orijen | puppy_food | Best Puppy Food UK - ID 3720 | pending_review | blocked_pending_evidence | not_verified | not_verified | not_verified | Premium pricing - price sensitivity for UK consumers; High-protein formulation controversy - some vets caution against very high protein for certain breeds; Biologically appropriate is a marketing term, not a regulated standard; No firsthand testing conducted
PE-009 | Harringtons Complete Dry Dog Food Chicken & Rice | Harringtons | dry_dog_food | Best Dog Food UK Hub - ID 3715, Best Dry Dog Food UK - ID 3717, Dry vs Wet Dog Food UK - ID 3719 | partial | blocked_pending_evidence | not_verified | not_verified | not_verified | Budget claims need actual comparative price data; Complete and balanced claims should be verified against current UK pet food regulations; No firsthand testing conducted
PE-010 | Lily's Kitchen Puppy Recipe Chicken & Salmon | Lily's Kitchen | puppy_food | Best Puppy Food UK - ID 3720 | pending_review | blocked_pending_evidence | not_verified | not_verified | not_verified | Puppy food - heightened responsibility for accuracy; Premium pricing may fluctuate significantly; Natural/organic claims need manufacturer attribution; No firsthand testing conducted
REGISTER INTEGRITY RULES:
- No fake testing claims
- No fake vet/expert endorsements
- No fake customer feedback
- No invented prices, ratings, or review counts
- All unverified claims explicitly marked
- All entries: approval_status = blocked_pending_evidence until verified
- 10 Dog Food entries populated. Cat Toys entries will be added when Cat Toys mission activates.

## Phase 8 Status Summary
# | Section | Status | Pass/Fail | Detail
1 | Co-Pilot RED-gate logic | FIXED + VERIFIED | PASS | _handle_next_publish() now filters out red_flag missions. Verified: returns 'Harness Product Schema' not insurance.
2 | Backlog agent assignments | FIXED | PASS | 55/65 items reassigned to correct agents using type-based rules.
3 | Backlog WP draft sync | FIXED | PASS | 5 backlog items linked to WP draft IDs (3715, 3717, 3719, 3720, 3722) with preview URLs.
4 | Pet Insurance target_cluster | FIXED | PASS | Corrected from pet_supplements to pet_insurance.
5 | Affiliate compliance (WP source) | VERIFIED | PASS | 15/15 pages have disclosure divs. 142/142 links have rel=sponsored. Agent parser has bug (not pages).
6 | Product Evidence Register | POPULATED | PASS | 10 Dog Food entries, all blocked_pending_evidence. No fake claims.
7 | Dog Food Draft QA | EXPORTED | PASS | 4 drafts with 15 QA fields each. Hub (3936w, 10/10), others framework-only.
8 | Pet Insurance RED Gate | VERIFIED | PASS | 12/12 RED gate checks pass. Content fully blocked until owner approval.
9 | Schema/Rich Results | PROPOSALS READY | PASS | Schema JSON-LD proposals created. Not deployed to WP yet (awaiting content approval).
10 | NOC/Operations | PARTIAL | PASS (with gaps) | 9/9 services active. Event bus, kill switch, recovery endpoints need routes. Backup fixed.
11 | Social degraded status | VERIFIED | PASS | All channels correctly show degraded/disconnected. Auto-posting blocked everywhere.
12 | GSC/GA4 source labels | VERIFIED | PASS | All outputs labelled: MODELLED FORECAST / ESTIMATED / PROXY SCORE. No live data connections.
13 | DLQ + Restore drill | FIXED + VERIFIED | PASS | Backup script fixed. Fresh backup (1.2MB). Restore drill: 291ms RTO, all files exact match.
14 | Timestamps/observability | VERIFIED | PASS | 0 NaN, 0 undefined. All ISO 8601 timestamps. No debug leakage.
OVERALL PHASE 8 STATUS: 14/14 sections addressed. 12 PASS, 2 PASS with noted gaps (NOC endpoints, affiliate agent parser).
REMAINING GAPS FOR PHASE 9:
1. Affiliate agent parser: Update BeautifulSoup logic to detect compound rel attributes and disclosure divs
2. Event bus status endpoint: Add health metrics to /api/events/status
3. Kill switch API route: Register /api/kill-switch/status on manager agent
4. Recovery drill endpoint: Consider adding /api/recovery/status
5. Content expansion: 3 Dog Food supporting pages need expansion from 300-340 words to 1500-2000 words
6. Cat Toys evidence: Product Evidence Register needs Cat Toys entries when mission activates